## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Zhiyuan Lin | 2024-03-15 | 2024-03-17 | 3 hours | 6 hours
Create Date dimension | Zhiyuan Lin | 2024-03-16 | 2024-03-19 | 1 hour | 1 hour
Create Province dimension | Zhiyuan Lin | 2024-03-16 | 2024-03-19 | 1 hour | 1 hour
Create vaccination dimension | Zhiyuan Lin | 2024-03-16 | 2024-03-19 | 1 hour | 1 hour
create a connection between python and postgre | Zhiyuan Lin | 2024-03-16 | 2024-03-19 | 3 hours | 3 hour
Create COVID19Metric dimension | Zhiyuan Lin | 2024-03-15 | 2024-03-17 | 3 hours | 3 hours
Staging of dimension Date | Lixiong Wei | 2024-03-17 | 2024-03-18 | 0.5 day | 1 day
Staging of dimension Province | Lixiong Wei | 2024-03-17 | 2024-03-18 | 0.5 day | 1 day
Staging of dimension Vaccination | Lixiong Wei | 2024-03-17 | 2024-03-18 | 0.5 day | 1 day
Staging of dimension COVID19 Metric | Lixiong Wei | 2024-03-17 | 2024-03-18 | 0.5 day | 1 day
Surrogate key pipeline | Lixiong Wei | 2024-03-19 | 2024-03-19 | 1 hour | 1 hour
Staging of fact table – including FKs and measures | Lixiong Wei | 2024-03-20 | 2024-03-20 | 1 day | 1 day
Data quality handling and reporting | Lixiong Wei | 2024-03-20 | 2024-03-19 | 3 hours | 2 hour
SQL statement design | Zhiyuan Lin | 2024-03-18 | 2024-03-19 | 3 hour | 8 hour