## Sheet1
CSI4142 - Project 2023
Phase 3- OLAP and BI Dashboard
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
OLAP queries | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
Drill down, roll up | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
Slice | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
Dice | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
Composite OLAP - 4 queries | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
Icebergs | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
Windowing - partition | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
Window | Lixiong Wei | 2024-04-01 | 2024-03-31 | two days | One and half day
BI dashboard | Zhiyuan Lin
Design of data mart | Zhiyuan Lin
Importing data | Zhiyuan Lin
OLAP queries | Zhiyuan Lin
Figures | Zhiyuan Lin
Other tasks - please specify