## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data summarisation | Lixiong Wei | 2024-04-03 | 2024-04-04 | 2 days | 3 days
.. Visualisation of attributes | Zhiyuan Lin | 2024-04-04 | 2024-04-04 | 1.5 days | 1.5 days
Data transformation | Lixiong Wei | 2024-04-04 | 2024-04-04 | 2 hours | 1 hour
.. Missing values | Proceed in phase 2 | Proceed in phase 2 | Proceed in phase 2 | Proceed in phase 2 | Proceed in phase 2
.. Categorical data | N.A | N.A | N.A | N.A | N.A | Explain in data_summarization.ipynb
.. Numeric data | Lixiong Wei | 2024-04-04 | 2024-04-04 | 2 hours | 1 hour
.. Feature selection | Zhiyuan Lin | 2024-04-04 | 2024-04-04 | 1 hour | 2 hours
Data mining - Classification | N.A | N.A | N.A | N.A | N.A | Not available for Classification
Decision tree | N.A | N.A | N.A | N.A | N.A | Not available for Classification
Gradient Boosting | N.A | N.A | N.A | N.A | N.A | Not available for Classification
Random Forests | N.A | N.A | N.A | N.A | N.A | Not available for Classification
Comparison of results | N.A | N.A | N.A | N.A | N.A | Not available for Classification
Summary | N.A | N.A | N.A | N.A | N.A | Not available for Classification
Anomaly detection
One-class SVM | Lixiong Wei | 2024-04-02 | 2024-04-03 | 3 hours | 12 hours
Summary | Zhiyuan Lin | 2024-04-03 | 2024-04-04 | 1 day | 2 days
Other tasks - please specify